## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | Majority of the customers ordered appetizers aside from their main dish. | 82% of the customers ordered appetizers
Customers | Went well | Most customers left a good review. | 40% of customers had a good experience with the tablet and 32% with great experience.
Customers | Went well | More than half of the customers were taught well by the waiters on how to use the tablet. | 76% of the customers answered very well when asked how they were instructed by the waiters on how to use the tablets.
Customers | Went well | Only few of the customers had a difficulty in navigating the tablets. | 30% of the customers felt neutral with the tablet navigation. While 4% said they had difficulty in using the tablets.
Customers | Went well | Few of the customers experienced difficulty in ordering using the tablet. | 28% of the customers are neutral when asked about the ease of ordering directly from the menu on the tablet, while 8% experienced difficulty.
Customers | Needs improvement | A little over half of the customers waited for more than 15 mins to get a table. | 54% of the customers waited more than 15 mins in order to get a table. | Discuss on how to keep wait times to a maximum of 15 minutes.
Customers | Needs improvement | More than half of the customers received their food within 20 mins. | On average, 56% of the customers received their food order within 20 mins. | Brainstorm on how to improve serving time.
Customers | Needs improvement | Most of the customers received correct orders. | When asked about the order accuracy, 72% of the customers said that the kitchen prepared your order correctly. | Still needs improvement, enhance the training of kitchen staff.
Customers | Needs improvement | Some customers experienced receiving wrong orders. | Here are some of the inaccuracies: (CS) - Wrong entree was brought out - Didn’t leave off the parsley - Didn’t leave off the cheese - Didn’t make the substitution I wanted - Entree was overcooked - I asked for a side of fries and got mashed potatoes | Seydou will check technical issue that’s affecting ticket accuracy.
Customers | Went well | The majority of the customers had a smooth checkout process. | 82% of the customers found that the checkout process is quick, easy, and secure.
Customers | Needs improvement | Some customers experienced issues during checkout process. | But there are some comments from the guests about the checkout process - I only had cash—didn’t realize I couldn’t use it so needed the waiter - The tablet froze, so it wasn’t quick - I wanted to pay in cash so the waiter needed to process it differently - It would be faster if I could just check out with my phone | Seydou will check technical issue on checkout process.
Customers | Went well | Some customers felt confident in making payments using the tablets. | 40% of the customers are confident in submitting their payment through a tablet.
Customers | Went well | Some customers wanted to make their payments using the tablets. | 40% of the guests liked the tablet experience better, and wanted to use it exclusively going forward.
Customers | Went well | The majority of the customers had a smooth overall experience using the tablet. | 88% of the guests didn’t experience technical issues with the tablet.
Customers | Needs improvement | Some customers experienced issues in using the tablet. | Some guests said they experienced issues on tablet: (4) - The screen froze - It was glitchy - It kept freezing but after the waiter did a reboot it was fine - It froze up a couple times | Seydou will check technical issue on tablet navigation.
Customers | Went well | We received good feedback about the implementation of tablets. | - The tablets were fun! - I liked the tablets - it felt like we got through our dinner faster - I liked the video about Sauce & Spoon on the tablet - The tablet were cool but I think we need to get used to them
Project team | Needs improvement | There is no significant change in the table turn time. | One area we could still improve is table turn time. We didn’t see as much of a decrease as we wanted to in that area - Gilly (Retrospective Meeting) | Brainstorm on how to improve table turn time.
Customers | Needs improvement | Some customers are requesting for the option of choosing the waiter. | - Please give us the option in the future of choosing a waiter. | Team will discuss the pros and cons of adding the waiter.
Project team | Went well | Tickets are coming through smoothly. | Tickets came through at a good pace and were easy to keep track of. - Zane (Retrospective Meeting)
Project team | Needs improvement | Some food orders were still incorrect and orders were sent back (less than before but still occuring). | There were still orders that got sent back. - Zane (Retrospective Meeting) | Still needs improvement, enhance the training of kitchen staff.
Project team | Went well | There were improvements done in kitchen operations as a result of new ticket flow. | Started implementing some updates to kitchen operations as a result of the new ticket flow, and we’re really happy with them - Larissa (Retrospective Meeting)
Project team | Needs improvement | There were few technical issues during the POS integration process. | We discovered a few technical issues during the POS integration process but able to address them quickly and get them fixed. There will always be routine maintenance issues that pop up - Seydou (Retrospective Meeting) | update the process manual so that the solution is easy to find next time that issue comes up
Project team | Went well | Successful survey data collection. | Results on survey indicate that we met most of our customer satisfaction standards. (Retrospective Meeting)
Customers | Needs improvement | The majority of our customers didn't join the Birthday Club. | 84% didn't sign up for the Birthday Club | working with the designer to update the content on the website and the tablets so it’s clearer what the program is, what we’re asking, and how people can participate
Project team | Needs improvement | There were operational issues that have been discovered upon launch of tabletop menu. | We discovered a few internal operational issues. (Retrospective Meeting) | We want to do a better job of understanding each location’s history before planning gets underway.
Project team | Needs improvement | The schedule of pilot launch took a little bit longer. | Tablet implementation took just a little bit longer than we hoped. There was some vacation time that was unaccounted for. (Retrospective Meeting) | make sure we plan things properly based on everyone’s availability
Project team | Needs improvement | Not prepared for the large volume of orders. | Everyone to be prepared to handle a larger volume of orders. (Retrospective Meeting) | help the back of house staff scale up their operations before the main launch
Project team | Needs improvement | Had a confusion on the responsibilities of front & back staff of the house. | Lack of understanding between what the front of house staff does and the back of house staff does. (Retrospective Meeting) | share those experiences it will help everyone work together more effectively
Project team | Needs improvement | Needed to enhance the waitstaff training process. | Waitstaff training process. (Retrospective Meeting) | develop a more comprehensive training session, or even break the training up into two parts
Customers | Went well | Most customers signed-up for newsletter. | 78% of the guests signed up for the newsletter on the tablet