## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: 1 Project Initiation
Create project charter |  | 4 | 4 | 5 | 6 | H
Allocate a budget for the project |  | 0
Schedule kick off meeting |  | 0 | 0 | 1 | 2 | H
General Manager meeting with waitstaffs to get buy-in |  | 1 | 1 | 2 | 3 | M
Milestone: 2 Preparation
Research tablet features. |  | 4 | 4 | 5 | 6 | M
Determine the number of tablets needed. |  | 1 | 1 | 2 | 3 | H
Establish technical requirements (e.g., Wi-Fi, power outlets). |  | 2
Check current POS version |  | 2
Contact electrician |  | 1
Milestone: 3 Vendor Selection
Research and select tablet hardware and software vendors. |  | 4 | 4 | 5 | 6 | H
Obtain price quotes and negotiate contracts. |  | 3 | 3 | 4 | 5 | M
Confirm compatibility of operating systems to POS system. |  | 4 | 4 | 5 | 6 | M
Order the required tablets and software licenses from Terrific Tablets and get it delivered |  | 8 | 7 | 8 | 9 | M
Milestone: 4 Menu Digitization
Revamp the menu | Still waiting on Carter for the finalized menu and coupon value mock-ups for upload (aiming for one week but could extend to two) | 9 | 7 | 11 | 14 | M
Create or digitize the restaurant’s menu items, including descriptions, prices and coupon add-ons | Once mock-ups are received, 3-4 hours to upload | 5
Record the guest modified menu items. |  | 2
Milestone: 5 Tablet Installation
Install the tablets in the restaurant. | Seydou projected 7-10 days shipping timeline, 3-4 hours to integrate the POS systems | 8 | 7 | 8 | 10 | H
Wire up the tables. | Electrician is confident they can wire both locations in two business days (16 hours), but since we can’t close the restaurants for a full day we need to schedule two half-days at each location | 3 | 2.5 | 3 | 4 | H
Connect tablets to the restaurant’s Wi-Fi network. |  | 1
Integrate tablets with POS software. | Possible need to upgrade the POS system if S&S is running an older version (3-4 days) | 3 | 1 | 3 | 5 | L
Test connectivity and functionality. |  | 3
Milestone: 6 Staff Training
Create a training schedule. | Gilly and Alex will coordinate with Peta to schedule staff trainings at each of their locations. Each part of the training (pre-training, manager training, staff training) will take place on different days. The preparations and planning for the trainings should take about one week. | 7 | 7 | 8 | 9 | H
Pre-training meeting | Pre-training meeting to introduce tablets and changes to staff before training them on the tablets (1 hour at each location) | 2 | 1 | 2 | 3 | H
Train key restaurant staff members on tablet usage. | Seydou will train managers first (2 hours), then managers will train all the staff at each location (2 hours for each training plus one hour before and after each training for facilitator prep/debrief) | 1 | 1 | 2 | 3 | H
Troubleshooting common issues. |  | 1
Handling customer inquiries about the tablets. |  | 1
Train restaurant staffs at each location. | Seydou will train managers first (2 hours), then managers will train all the staff at each location (2 hours for each training plus one hour before and after each training for facilitator prep/debrief) | 1 | 1 | 2 | 3 | H
Milestone: 7 Testing and Quality Assurance
Conduct a test run with family and friends. |  | 1 | 1 | 2 | 3 | H
Conduct extensive testing of the tablets and menu software. |  | 2
Identify and resolve any technical or usability issues. |  | 2
Gather feedback from the staff and make necessary adjustments. |  | 1
Milestone: 8 Marketing and Promotion
Develop a marketing strategy to inform customers about the new tablets. |  | 3 | 3 | 4 | 5 | H
Update the restaurant’s website and social media profiles. |  | 4 | 4 | 5 | 6 | H
Create promotional materials and special offers. |  | 3 | 3 | 4 | 5 | H
Milestone: 9 Launch and Monitoring
Create launch date plan, staffing and troubleshooting. |  | 7 | 7 | 8 | 9 | H
Officially launch the tablet menu system. |  | 1
Implement a post-dining survey to assess customer satisfaction |  | 1
Address any issues or concerns promptly. |  | 1
Regularly updating the menu via software |  | 3
Continuously assess the performance of the tablets and make improvements as necessary. |  | 1
Milestone: 10 Maintenance and Support
Implement a maintenance plan to keep tablets and software up to date. |  | 5 | 5 | 6 | 7 | H
Provide ongoing support for staff and customers. |  | 1
Regularly assess the impact of the tablets on restaurant operations and customer satisfaction. |  | 2
Milestone: 11 Evaluation and Reporting
Evaluate the success of the tablet rollout against predefined objectives. |  | 2
Generate reports on key performance indicators (KPIs). |  | 2
Make informed decisions for future improvements or expansions. |  | 1
Milestone: 12 Continuous Improvement
Gather ongoing feedback and make necessary adjustments. |  | 1
Expanding tablet menu to other areas of the restaurant. |  | 5
Milestone: 13 Project Closure
Conduct a project review to document lessons learned. |  | 2
Complete any outstanding administrative tasks. |  | 1
Celebrate the successful rollout of the tablet menu system. |  | 1